## RESET OCT22
Diversity Mark project management process for SSCT
STEP 1: Presentations to Divisions to promote Diversity Mark
Introduction Presentation from DO and SDMO Diversity Mark
Convenor registers interest
Request Convenor email the Student Success Project email address to register interest in putting module through the Diversity Mark process
DM Project Manager to process notification of interest
DM PM Respond with templated email and maintain the 'Waiting List' document
Request convenor completes the 'Intent and Consent' form
Sign post Diversity Mark on Student Success website
Including articles written by DM Research Associates et al
Including SSUN Meeting Presentation RECORDINGS – to be added to website
When ready: Case studies to be requested from Ben, Angela, Iain, etc.
On receipt of Convenor 'Intent and Consent' Form
DM PM to manage Waiting List
DM PM to send TEMPLATE email 'Introduction Bundle' to Convenor including:
DM Process for Convenors document
One Pager - 'What is Diversity Mark?'
Link to Library Toolkit
When ready: DM Moodle page
INCLUDE Suggested preparation work for Module Convenor before working with DMO
Library resources – Workshop session (as Drill Hall)
Library resources – Retreat (as Emma M-R and Sarah F)
Attend ‘Reflective Teaching’ session – ran by their Division / Subject Area
Convenor to identify work carried out to date to diversify module (whilst on the Waiting List)
When ready: Recommendations of what convenors can do to prepare their module (TBC list and/or video SDMO)
Confirmation of schedule
DM PM to manage communications with convenors on waiting list to keep convenors 'warm' and track progress
DM PM to manage waiting list and contact with Convenors when availability with DMO
Agree timeline with statement of commitment from Module Convenor
DM PM to assign module to DMO (and SDMO for oversight)
Working with a Diversity Mark Officer
Module Convenor provides access to module to DMO & SDMO
DM PM and SDMO to initiate meeting between DMO and Convenor
Convenor introductory meeting
DIVERSITY MARK MAP OF THE MODULE - DMO to produce a review report reflecting analysed data of all of the reading material in the module (core readings of reading list, weekly lectures and seminar materials, talks, presentations, discussions, assignments)
DMO to review with SDMO
DMO to present findings to Module Convenor followed by in depth discussion with the convenor
DMO to produce recommendations (with specific examples) and next steps POA together with the convenor. Ensure Convenor approves and agree timeline to implement the POA
Convenor to implement application and actioning of recommendations
DMO to set up Focus Groups
Involving Student voice - co producers of knowledge
DMO to plan a Student Focus Group to gather information from students - where possible, collaborate with another DMO to discuss opportunities for discussion. Make sure there are specific themes related to the module where you would like the students' involvement to be visible.
Process the results of the FG and provide evidence to the Convenor - allow the convenor to agree on implementing the concrete improvements / adjustments as suggested by the student.
Working with the Library / ALS
Apply suggested recommendations to reading list
Set up Padlet (online virtual bulletin board) to be inserted in Moodle
Establish a feedback mechanism for informing students what is done with Padlet submissions
Preparing for submission to panel review
Once all of the steps on the POA have been implemented produce tangible evidence - FG transcript, report of library session done, student examples recommended,
Convenor and DMO to complete application form together
Include 'Checklist' for Convenor to submit along with application
Include 'Questionaire' reflecting the challenges and opportunitie of the module
The Convenor to submit DM award application
DM panel review
DM PM to amange Awarding Panel members and timeline
DM PM to manage application forms and Awarding panel process
DM PM to set up Awarding Panel meetings to plan and review applications
Post DM panel review
DM PM to contact Convenor to let them know the outcome of their application
DM PM to send Report of recommendations to Convenor and SDMO - this may be a PASS or REFERAL
DM PM to manage progress of Modules not achieving DM Award status
Post DM panel review accreditation
DM PM to email Widget including details of achievement and year awarded or updated added to module Moodle page
DM PM to send 'Email Signature Template including DM Status module convenor and module
DM PM to organise Certificate - module convenor and module
DM PM to set up and manage DM Awards ceremony

## Sheet1
Introduction Presentation from DO and SDMO Diversity Mark | Template / documentation / link to location
Presentations with Divisions to promote DM
Convenor to register interest | Template / documentation / link to location
Promote Diversity Mark on Student Success website | studentsuccessproject@kent.ac.uk
Request Convenor email the Student Success team to register interest in putting module through the Diversity Mark process by completing the Intent and Consent form which can be found at this location (website) | LOCATED: DM TEMPLATES AND FORMS MASTERS / DM_Intent and consent form 2022_FINAL
AM to EMAIL INTRODUCTION TO DM BUNDLE INCLUDING | Template / documentation / link to location | ACTION REQUIRED 12th AUG 2022
Step by Step document with timeline end to end process | DRAFT 1 LOCATED: DM Process for Convenors / DM Process for Convenors_Draft v1 | Draft in progress - Kerry
Template email to send out with process doc | INTRODUCTION BUNDLE FOR CONVENOR / DM_Email Introduction to Convenor
One Pager - 'What is Diversity Mark?' | DRAFT 1 LOCATED: DM TEMPLATES AND FORMS MASTERS / INTRODUCTION BUNDLE FOR CONVENOR / Diversity Mark One Pager_WIP Draft v1 | Draft in progress - Kerry / Sign off from Barbara to follow
Link to Student Success Website | https://www.kent.ac.uk/student-success/diversity-mark | check all pages are current and links are to correct documentation, copy is correct, UPDATE awards have been given out, add case studies,
Including SSUN Meeting Presentation RECORDING |  | SSUN Meeting BOOKED 11th October - Rachel and Ben Turner agreed to be recorded
Case studies - NEW DOCUMENT(s) |  | Kerry to liaise with Angela Harrison and Ben Turner
DM Moodle page - NEW (to be discussed after agreeing process) |  | Alison Webb, Library (Sarah and Emma) and Senior DMO & Dos - added to SSCT Operation Plan
Suggested preparation work for Module Convenor before working with DMO | Template / documentation / link to location | ACTION REQUIRED 12th AUG 2022
Template email to send to Convenor to acknowledge receipt of Intent Consent form and placement on waiting list | INTRODUCTION BUNDLE FOR CONVENOR / DM_Email Acknowledgement of Intent Consent to Convenor
Library resources - ALS 'training' sessions | Meeting with Divisional Liaison Librarians on 17th October 2pm | Speak to ALS about training / support approach
Library Website toolkit link
Convenor to identify work carried out to date to diversify module (whilst on the Waiting List) |  | How is this recorded? Template?
Reccomendations of what convenors can do to prepare their module | Senior DMO to produce video | Speak to Rachel re producing a video
| Library to produce video? | Speak to DLL Team
Confirmation of schedule | Template / documentation / link to location | ACTION REQUIRED 12th AUG 2022
Convenor to email Student Success Project email address to confirm when ready to start process and what stage they are up to in diversifying their module
Agree timeline with statement of commitment from Module Convenor | Diversity Mark 2022-23 | WAITING LIST MANAGEMENT - needs process / plus template email and confirmation of commitment to dates offered from Convenor
https://livekentac.sharepoint.com/:x:/r/teams/StudentSuccessProject-CentralTeam/_layouts/15/Doc.aspx?action=edit&sourcedoc=%7Bae704caf-8b87-4b3b-a739-ea6bc6b70f99%7D&wdOrigin=TEAMS-ELECTRON.teamsSdk.openFilePreview&wdExp=TEAMS-CONTROL
AMs to Assign module to DMO with progress update handover to DO | MONTHLY TAB UPDATES (see Diversity Mark 2022-23 spreadsheet) | Development Officer - DMO Schedule MANAGEMENT - monthly updates
Working with a Diversity Mark Officer | Template / documentation / link to location | ACTION REQUIRED 12th AUG 2022
Module Convenor provides access to module to DMO
Development Officer to initiate meeting between DMO and DO
Convenor introductory meeting | Presentation slide deck | Presentation may need refreshing, it must align to current process and aims (check with DO's/DMO's)
PRODUCE A DIVERSITY MARK MAP OF THE MODULE - DMO to produce a review report reflecting analysed data of all of the reading material in the module (core readings of reading list, weekly lectures and seminar materials, talks, presentations, discussions, assignments) | Rachel has template - ADD TO NEW FOLDER | Time line really varies depends on the module and module content - 10 weeks seminars, overall - approx a month
DMO to present findings to Module Convenor - discuss DM Map with the convenor - in depth | Presentation - speak to Rachel
DMO to produce recommendations (with specific examples) and next steps POA together with the convenor. Make sure the Convenor is content with the follow ups and agree on a aset timeline to implement the POA. | Plan of Action template
The convenor now has the opportunity to work on applying and actioning the recommendations - whilst the DMO runs Focus Group
Involving Student voice - co producers of knowledge | Template / documentation / link to location | ACTION REQUIRED 12th AUG 2022
DMO to plan a Student Focus Group to gather information from students - where possible, collaborate with another DMO to discuss opportunities for discussion. Make sure there are specific themes related to the module where you would like the students' involvement to be visible. | Use Tamika's document to give guidance for operational planning setting up arranging the FG - write tailored FG questions based on themes and gaps in module - Rachel to provide training
Process the results of the FG and provide evidence to the Convenor - allow the convenor to agree on implementing the concrete improvements / adjustments as suggested by the student.
Working with the Library / ALS | Template / documentation / link to location | ACTION REQUIRED 12th AUG 2022
Apply suggested recomendations to reading list | Meeting with Divisional Liaison Librarians on 17th October 2pm | Speak to ALS about training / support approach
Set up Padlet (online virtual bulletin board) to be inserted in Moodle
Establish a feedback mechanism for informing students what is done with Padlet submissions
Preparing for submission to panel review | Template / documentation / link to location | ACTION REQUIRED 12th AUG 2022
Once all of the steps on the POA have been implemented produce tangible evidence - FG transcript, report of library session done, student examples recommended, | PRODUCE A CHECKLIST OF TYPES OF EXAMPLES THAT SHOULD BE PROVIDED
Convenor and DMO to complete application form together | LOCATED: DM TEMPLATES AND FORMS MASTERS / DM_Application Form 2022 FINAL
The Convenor then submits a DM award application, including a questionaire reflecting the challenges and opportunities of the module | PRODUCE A CHECKLIST OF DOCUMENTS TO BE SUBMITTED Speak to Rachel re POST PROCESS Questionaire
DRAFT 1 LOCATED: DM TEMPLATES AND FORMS MASTERS /DM module convenor application invite Jan2022
DM panel review
Set up a new Panel of new members
Agree dates for Panel Review (Feb) and Awarding Celebration (July Learning & Teaching Conference)
Log any completed modules that come through to SSCT shared inbox | DRAFT 1 LOCATED: DM TEMPLATES AND FORMS MASTERS / DM_Awarding Panel | Work with DO team - schedule meeting to discuss approach
Alert panel members that there is 1 month until the next panel Review meeting and advise when submitted modules are ready for panel review on Teams folder | DRAFT 1 LOCATED: DM TEMPLATES AND FORMS MASTERS / DM_Applications ready for review email
Circulate Panel Guidance Document | DRAFT 1 LOCATED: DM TEMPLATES AND FORMS MASTERS / Diversity Mark Panel Guidance Feb 2022
Set up meeting for Panel Members to review applications
Post DM panel review
Contact Convenor to let them know the outcome of their application |  | Bec to liaise with Hollie, move forms to the folder
Send Report of recommendations to Convenor - this may be a PASS or REFEREAL |  | Bec to liaise with Hollie, move forms to the folder
If the Module did not achieve DM Award status - we need to check on Progress on recommendations update
Post DM panel review accreditation
DOs to email Widget including details of achievement and year awarded or updated added to module Moodle page |  | Bec to liaise with Hollie, move to the folder
DOs to Email signature - module convenor and module |  | Bec to liaise with Hollie, move to the folder
Certificate - module convenor and module | Certificate template | Administrator - Creating Certificates, ordering frames, coordinating signature from RR
Awards ceremony - Teaching Excellence Awards ceremony - awards distributed |  | Who will introduce DM? Is this BA? Who will present awards - is this Louise Naylor, where will this be held, etc
Post DM accreditation updates and monitoring
Phase 2
Post DM accreditation updates and monitoring
How to keep Accrteditation up to date - how do we refresh awarding?